## Notes
L | F | Lipedema Foundation www.lipedema.org | Awardee-Committed Project Activities, Milestones & Deliverables
|  | draft version # | 1 <- increment this, if you wish
Usage
This schedule and statement of deliverables will be incorporated into future progress reports, and will be periodically reviewed with awardees.
This document represents a summary of the timeline of the award and specific work products that will be delivered to the Lipedema Foundation or research community.
These commitments are agreed to by signing the Sponsored Research Agreement
Instructions
One the next page, fill out the Milestones, Deliverables, & Project Schedule worksheet, noting key milestones and specific deliverables. All items should relate directly to the written descriptions of your aims.
If a task is important to include, but does not fit a definition of being a milestone or deliverable, simply leave column B blank.
An example is provided on the final page of this document.
This file will be uploaded with your proposal.
Definitions
Milestones refer to activities whose completion can be used to assess project progress. Achievement of milestones answers the question "Is the project on track to produce its deliverables?"
Deliverables imply specific work products that will be created during the course of the project. Achievement of the deliverables answers the question "Did the project accomplish what it set out to do?"
Consider the following milestones and deliverables:
Example Milestones
• IRB/ethics committee and/or IACUC approved
• staff hired and/or training completed
• research protocols optimized
• samples procured, or study participants enrolled
• data analysis completed
Example Deliverables
• Confirmation to LF citing an ethics approval
• Manuscript(s), presentations
• Data or resource made available to others vis sharing
• Creation of prototypes, or study protocols, regulatory filings, etc.
Amendments
At the time of award:
Should your proposal receive an Lipedema Foundation award offer, the timelines as stated may be subject to modification before an award can be executed. In some cases, the Lipedema Foundation may require deliverables of intermediary products. For instance, the Foundation may require review of IRB consent language or similar regulatory documentation in order to comply with insurance and internal requirements. Agreed changes will be incorporated into the award documentation.
During the course of the award:
As new data emerges the research plan may require modification. Such changes must be agreed with the Lipedema Foundation. Once agreed, the changes will be incorporated into an official amendment to this document. The amended timeline will replace the original for use in progress reporting.
LF template version #2.0 do not edit

## Milestones, Deliverables, and S
|  | Planned state date: |  | Study Year 1 |  |  |  | Study Year 2
Planned end date:
Related Aim(s) | Milestone or Deliverable? | Description | Responsible Site | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Notes
x
The above cells are conditionally formatted.
Entering any text in a cell will automatically color the cell as shown
See next worksheet for example

## Example
|  | Planned state date: | 2021-10-01 |  | Study Year 1 |  |  |  | Study Year 2
|  | Planned end date: | 2023-09-30
Related Aim(s) | Milestone or Deliverable? | Description tasks | Responsible Site | Milestone or Deliverable? | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Notes
All | Deliverable | PI emails LF confirmation that IRB was approved | Site X | Milestone | x
All | Milestone | MTA/Legal agreements complete | Site x,y | Milestone |  | x | [6 empty] | Template agreements already exist between these two laboratories
All | Milestone | Postdoc hired & trained | Site X | Milestone |  | x
Aims 1, 2 | Milestone | Site 1 recruitment | Site X | Milestone |  |  | x | x | x |  |  |  | See Figure 1 for details
Aims 1, 2 | Milestone | 50% recruitment at site 1 | Site X | Milestone |  |  |  | x
Aim 1a |  | Optimize method 1 for candidate marker detection | Site X | Milestone |  |  | x | x
Aim 1b | Milestone | Method 1 analysis on patient samples completed | Site X | Milestone |  |  |  |  | x
Aim 1c | Milestone | Tissue samples delivered to Dr. Y site | Site X | Milestone |  |  |  | x
Aim 1c | Milestone | Replicate of 1b at Dr. Y site | Site Y | Milestone | [5 empty] | x
Aim 2a |  | Optimize method 2 for candidate marker detection | Site X | Milestone |  |  |  | x | x
Aim 2b | Milestone | Method 2 analysis on patient samples | Site X | Milestone | [5 empty] | x
Aim 2c | Milestone | Replicate of method 2 at Dr. Y site | Site Y | Milestone | [5 empty] | x
All | Milestone | Statistical analysis of both methods completed | Site X | Milestone | [6 empty] | x |  | This will be performed by Dr. Smith
All | Deliverable | Residual tissue contributed to Biobank | Site X,Y | Deliverable | [7 empty] | x
All | Deliverable | Data shared with Lipedema Foundation | Site X,Y | Deliverable | [7 empty] | x
All | Deliverable | Manuscript preparation and submission | Site X,Y | Deliverable | [7 empty] | x
All |  | Manuscript published | Site X,Y | Deliverable | [7 empty] | x
The above cells are conditionally formatted.
Entering any text in a cell will automatically fill the cell as shown